## What_It_Proves
Rempo go-to-market · 90-Day Experiment
What It Proves. Skill phase: Phase 10 (added). Source: dashboards/10-90-day-experiment.md (Run 2, 2026-10-19).
What the experiment has to prove
1. That home-service owners buy a done-for-you review service from a VSL page without a call, at $197 a month plus setup (the founder's core hypothesis, now the funnel's design).
2. What a paying customer costs, against the $350 working CAC.
3. Which hook leads: done for you, the personalized request, or every review answered.
4. How much the bumpers carry: the share of buyers who come through a call or the scorecard instead of buying straight from the page.
5. Whether the CRM gate costs too many sales.
6. Whether personalized requests beat plain ones, and when to send the first ask, inside real accounts.

## Budget
Rempo go-to-market · 90-Day Experiment
Budget. Skill phase: Phase 10 (added). Source: dashboards/10-90-day-experiment.md (Run 2, 2026-10-19).
The $15,000 allocation (recommendation)
Line | Month 1 | Month 2 | Month 3 | Total | Share
Meta ads (VSL, scorecard, retargeting) | 1500 | 2000 | 2500 | 6000 | 40%
Google Search ads | 800 | 800 | 800 | 2400 | 16%
Media buyer plus research strategist | 900 | 900 | 900 | 2700 | 18%
Creative: VSL edit, ad videos | 1000 | 400 | 400 | 1800 | 12%
Tools: scorecard, geo-grid tracker, call recording | 200 | 200 | 200 | 600 | 4%
Reserve: scale the winning hook after day 60, or fund the founding cohort's setup credits | 0 | 0 | 1500 | 1500 | 10%
Total | 4400 | 4300 | 6300 | 15000 | 100%
Not funded: the creative agency ($7,200 over 90 days, 48% of the budget); SEO at $500 a month (results arrive after the window); the product layer (Phase 11 holds it).

## Week_0
Rempo go-to-market · 90-Day Experiment
Week 0. Skill phase: Phase 10 (added). Source: dashboards/10-90-day-experiment.md (Run 2, 2026-10-19).
Week 0, before any spend
• The offer goes live: one plan card, add-ons, "three or more locations? Book a call", the paid start and guarantee, "24/7 Support" removed (Phase 9).
• The funnel core exists: VSL, VSL page, FAQ, checkout with qualifier and bump, upsell page, thank-you and booking, call page, scorecard (Phase 8). Built outside this run.
• Tracking events: ad click, VSL page view, video progress (25%, 50%, offer reached), each call to action, checkout start, qualifier answers, purchase, bump, upsell, onboarding booked, software connected, first request sent. UTM tags on every ad.
• Proof capture, before the first customer: the permission clause in the terms; the baseline (Phase 0, Step 0.7); consent for the request-style comparison.
• Founder capacity: the most onboarding and sales calls a week the founder can run beside the day job, {TBD}, set before launch.
• Decision floors, set before day 1 and not after seeing data: month-2 retention floor {TBD}; target share of purchases without a call {TBD}.

## Tests
Rempo go-to-market · 90-Day Experiment
Tests. Skill phase: Phase 10 (added). Source: dashboards/10-90-day-experiment.md (Run 2, 2026-10-19).
The tests (one variable each)
Test | Variants | Measure | Runs
Hook | A "We run your Google reviews from your job software." B "Here's what your customer sees." (the personalized request) C "Every review answered, every job asked." | Cost per purchase; VSL completion to the offer | Meta, weeks 1 to 6
Entry | Ads straight to the VSL page against ads to the scorecard first | Cost per purchase within 30 days of first click | Meta, weeks 3 to 10
Request style | Personalized image against plain text, alternating by customer within each consenting account; every customer is still asked | Request-to-review rate against the account's baseline | Inside accounts, 30 days each
First-ask timing | Same day as the job against day 3 | Request-to-review rate | Inside accounts, after the style test
Start | Paid start with guarantee (default). A 15-day trial only if the gate below trips | Checkout conversion; refunds; unpaid setup hours | From day 60, if triggered

## Gates
Rempo go-to-market · 90-Day Experiment
Gates. Skill phase: Phase 10 (added). Source: dashboards/10-90-day-experiment.md (Run 2, 2026-10-19).
Definitions
• Paid CAC: paid media spend ÷ new paying customers from paid channels, by cohort.
• Self-serve share: purchases with no sales call before them ÷ all purchases.
• Payback months: paid CAC ÷ monthly subscription revenue of the plans bought.
• Minimum data before judging an ad set: about twice the CAC hurdle in spend ($700), a working rule of thumb.
Gates and decision rules
Thresholds come from payback arithmetic on the front-end price ($197 a month), so they hold before any bump or upsell revenue is proven. Recompute at Gate 2 with measured take rates.
Band | Payback | Front-end CAC
Green | 3 months or less | $591 or less
Yellow | 3 to 6 months | $591 to $1,182
Red | More than 6 months | More than $1,182
The founder's $350 working CAC sits inside green; reaching it is the stretch goal.
Gate | When | What is known by then | Decision rule
Gate 1 | Day 30 | First purchases; VSL completion; qualifier failure rates; first days-to-first-request | Red, or no purchase after $1,500 in a channel: change the hook or the VSL opening before spending more. Qualifier failure above {TBD} on the CRM question: name the supported software in every ad
Gate 2 | Day 60 | Two cohorts; hook test read; entry test under way; bump and upsell take rates | Red on a channel: stop it and move its budget. Green and at or below $350: scale with the reserve. Checkout starts high but purchases low, with price or "free trial" named in abandoned-checkout replies: run the Start test
Gate 3 | Day 90 | Three cohorts; month-2 retention of cohort 1; self-serve share; request-style results | Success and stop criteria below
Success and stop criteria
Success at day 90 (all four):
1. Blended paid CAC in green.
2. Self-serve share at or above the floor set in week 0.
3. Median days from software connection to first request of 7 or fewer (the guarantee holds).
4. Month-2 retention of the first cohort at or above the floor set in week 0.
Stop paid media if no channel reaches yellow by day 60. Put the remaining budget into the founding cohort's results and the scorecard list, and rework the VSL and offer before spending on ads again.
Stop selling without a call if the self-serve share is below half the floor at day 60 and call-to-purchase is green: the funnel keeps the VSL, but "Book a call" becomes the primary call to action until the page is reworked.

## Capacity_and_Scorecard
Rempo go-to-market · 90-Day Experiment
Capacity and Scorecard. Skill phase: Phase 10 (added). Source: dashboards/10-90-day-experiment.md (Run 2, 2026-10-19).
Capacity rule
When booked onboarding and sales calls reach the founder's weekly cap, stop increasing ad spend and route the overflow to assistant-led onboarding: a recorded walkthrough plus a call with the assistant. If assistant-led onboarding activates accounts as well as the founder's calls, the cap stops limiting growth.
Weekly scorecard
Spend by channel; click-through rate; cost per VSL page visit; VSL completion to the offer; clicks on each call to action; checkout starts; qualifier failures by question; purchases; self-serve share; bump and upsell take rates; calls booked, held, and converted; scorecard opt-ins and purchases from the list; paid CAC and payback band; onboarding booked within 24 hours; days to first request; ask coverage; reply coverage; request-to-review rate by style and timing; month-2 retention once cohort 1 reaches it; founder hours on calls.

## Legend
Rempo go-to-market · 90-Day Experiment
Legend: what the colors mean, and the dropdown lists
• Colors are conditional-formatting rules, not painted cells: change a value, or pick another option from a dropdown, and the color follows.
• Header rows are royal blue. Rempo's own row or column is tinted brand blue, so it is easy to find in every comparison.
• Orange marks the done-for-you service (the front-end offer and its upsells); violet marks the product layer behind it.
• Blue numbers on a pale yellow fill are inputs you can change; black numbers are formulas and recalculate.
Colors used in this workbook
Looks like | Means | Where
Rempo | Rempo's own row or column | Every comparison table
{TBD} | Unknown until Rempo has its own data. Never invented. | Any cell; the color clears when the text is replaced
Green | Payback band (whole row) | Gates
Yellow | Payback band (whole row) | Gates
Red | Payback band (whole row) | Gates